12 Mar FAIRDASH

---

FairDash Platform Audit Report

Date: March 12, 2026 | Deadline: June 1, 2026 | Time Remaining: ~11 weeks

---

Executive Summary

FairDash is a polished, production-quality frontend mockup with zero operational capability. The UI is genuinely good — the design system is

consistent, Clerk auth works, the cart functions, and the vendor dashboard UI has been built — but every system that makes a delivery platform

actually work is completely absent. No backend. No database. No real-time layer. No payments. At the current trajectory, you are approximately 17%

complete overall. With 11 weeks to the June 1 deadline and roughly 3 months of backend work remaining, the timeline is critically at risk.

---

1. CODEBASE INVENTORY

File Tree Summary

fairdash-app/                    ← frontend-only

├── src/

│   ├── components/  (14 files)  ← UI components only

│   ├── pages/       (12 files)  ← all frontend pages

│   │   └── vendor/  (1 file)   ← VendorDashboard.jsx (UI only)

│   ├── context/     (2 files)  ← CartContext, MobileMenuContext

│   ├── hooks/       (1 file)   ← useMediaQuery

│   └── utils/       (3 files)  ← vendorData.js, menuData.js, vendorPortalData.js

├── design-system/MASTER.md      ← design reference

├── .env                         ← Clerk + Google Maps keys only

├── package.json                 ← 8 runtime deps, no backend deps

└── [NO backend/, server/, api/, db/]

Technology Stack — Verified

┌─────────────────────────┬───────────┬─────────┬───────────────────┐

│          Layer          │ Installed │ Version │      Status       │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ React                   │ ✅        │ 18.2.0  │ Working           │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Vite                    │ ✅        │ 5.0.8   │ Working           │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Tailwind CSS            │ ✅        │ 3.4.19  │ Working           │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Clerk Auth              │ ✅        │ 5.60.1  │ Working           │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ React Router            │ ✅        │ 6.20.0  │ Working           │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Google Maps             │ ✅        │ 1.7.1   │ Autocomplete only │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ react-hot-toast         │ ✅        │ 2.6.0   │ Working           │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Heroicons + react-icons │ ✅        │ Latest  │ Working           │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Firebase                │ ❌        │ —       │ Not installed     │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Stripe                  │ ❌        │ —       │ Not installed     │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Express/Fastify/Next.js │ ❌        │ —       │ Not installed     │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Prisma/Drizzle/Supabase │ ❌        │ —       │ Not installed     │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Recharts                │ ❌        │ —       │ Not installed     │

├─────────────────────────┼───────────┼─────────┼───────────────────┤

│ Socket.io/Pusher        │ ❌        │ —       │ Not installed     │

└─────────────────────────┴───────────┴─────────┴───────────────────┘

---

2. FEATURE COMPLETION MATRIX

Customer App — 28% complete

┌──────────────────────────┬─────────┬────────────────────────────────────────────────────────┐

│         Feature          │ Status  │                         Notes                          │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Browse vendors/menu      │ ✅ 100% │ Hardcoded data, fully browsable                        │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Cart (add/remove/modify) │ ✅ 100% │ localStorage, works well                               │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Clerk authentication     │ ✅ 100% │ Login, OAuth, protected routes                         │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Address autocomplete     │ ✅ 80%  │ Google Maps, no delivery zone validation               │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Checkout UI              │ ✅ 60%  │ Form exists, payment section is placeholder icons only │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Guest checkout flow      │ ❌ 0%   │ No implementation                                      │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Multi-vendor cart        │ ⚠️  10%  │ Cart exists but no vendor conflict logic               │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Live order tracking      │ ❌ 0%   │ /track route exists, page not found in scan            │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Order history + reorder  │ ❌ 0%   │ No order storage anywhere                              │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Sold-out item handling   │ ❌ 0%   │ No inStock field on menu items                         │

├──────────────────────────┼─────────┼────────────────────────────────────────────────────────┤

│ Push notifications       │ ❌ 0%   │ No service worker, no Firebase                         │

└──────────────────────────┴─────────┴────────────────────────────────────────────────────────┘

Vendor Dashboard — 22% complete

┌──────────────────────────────────────┬─────────┬────────────────────────────────────────────┐

│               Feature                │ Status  │                   Notes                    │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Dashboard UI shell                   │ ✅ 100% │ VendorDashboard.jsx (33KB) fully built     │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Stats cards (revenue, orders)        │ ✅ 100% │ UI complete, data is mock                  │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Orders table with statuses           │ ✅ 80%  │ UI built, vendorPortalData.js mock data    │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Status progression buttons           │ ⚠️  20%  │ UI buttons present, no real logic/timers   │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Menu management UI                   │ ⚠️  30%  │ Likely in dashboard, no backend CRUD       │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Two-step acceptance (90s/2m timers)  │ ❌ 0%   │ No timer logic, no enforcement             │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Sold-out toggle (instant)            │ ❌ 0%   │ No real-time toggle to any DB              │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ "Busy" status (15-min auto-clear)    │ ❌ 0%   │ No implementation                          │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ "Notify Fair Dash" button (Option B) │ ❌ 0%   │ No implementation                          │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Tablet-optimized layout              │ ⚠️  40%  │ Responsive CSS exists, not tablet-specific │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Audible alert on new orders          │ ❌ 0%   │ No audio API, no push mechanism            │

├──────────────────────────────────────┼─────────┼────────────────────────────────────────────┤

│ Real data (not mock)                 │ ❌ 0%   │ 100% mocked via vendorPortalData.js        │

└──────────────────────────────────────┴─────────┴────────────────────────────────────────────┘

Driver App — 12% complete

┌─────────────────────────────┬────────┬────────────────────────────────────────────┐

│           Feature           │ Status │                   Notes                    │

├─────────────────────────────┼────────┼────────────────────────────────────────────┤

│ BecomeDriver onboarding UI  │ ✅ 85% │ 23.5KB wizard, mirrors BecomeVendor        │

├─────────────────────────────┼────────┼────────────────────────────────────────────┤

│ Driver login                │ ✅ 50% │ Clerk handles auth, no driver role scoping │

├─────────────────────────────┼────────┼────────────────────────────────────────────┤

│ Go-active toggle            │ ❌ 0%  │ Not built                                  │

├─────────────────────────────┼────────┼────────────────────────────────────────────┤

│ Two-leg navigation          │ ❌ 0%  │ No GPS nav integration                     │

├─────────────────────────────┼────────┼────────────────────────────────────────────┤

│ Pickup/dropoff confirmation │ ❌ 0%  │ No implementation                          │

├─────────────────────────────┼────────┼────────────────────────────────────────────┤

│ Return to staging prompt    │ ❌ 0%  │ No implementation                          │

├─────────────────────────────┼────────┼────────────────────────────────────────────┤

│ GPS tracking                │ ❌ 0%  │ No geolocation → backend reporting         │

├─────────────────────────────┼────────┼────────────────────────────────────────────┤

│ Order matching/dispatch     │ ❌ 0%  │ No algorithm                               │

└─────────────────────────────┴────────┴────────────────────────────────────────────┘

Fair Admin Portal — 0% complete

┌─────────────────────────────────────┬────────┬────────────────────────┐

│               Feature               │ Status │         Notes          │

├─────────────────────────────────────┼────────┼────────────────────────┤

│ Event setup wizard                  │ ❌ 0%  │ No admin portal exists │

├─────────────────────────────────────┼────────┼────────────────────────┤

│ Delivery model selector             │ ❌ 0%  │ No implementation      │

├─────────────────────────────────────┼────────┼────────────────────────┤

│ Live dashboard (orders/revenue/GPS) │ ❌ 0%  │ No implementation      │

├─────────────────────────────────────┼────────┼────────────────────────┤

│ Vendor management (toggle on/off)   │ ❌ 0%  │ No implementation      │

├─────────────────────────────────────┼────────┼────────────────────────┤

│ Driver management + GPS map         │ ❌ 0%  │ No implementation      │

├─────────────────────────────────────┼────────┼────────────────────────┤

│ Post-event report generation        │ ❌ 0%  │ No implementation      │

├─────────────────────────────────────┼────────┼────────────────────────┤

│ Stripe payout triggering            │ ❌ 0%  │ No implementation      │

└─────────────────────────────────────┴────────┴────────────────────────┘

Backend / Infrastructure — 0% complete

┌───────────────────────────────────┬────────┬──────────────────────────┐

│              Feature              │ Status │          Notes           │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ Database schema                   │ ❌ 0%  │ No database of any kind  │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ API endpoints                     │ ❌ 0%  │ No server, no routes     │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ Stripe Connect (Express accounts) │ ❌ 0%  │ Not installed            │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ Firebase Realtime Database        │ ❌ 0%  │ Not installed            │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ Two-step vendor acceptance logic  │ ❌ 0%  │ No backend to run timers │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ Auto-cancellation with refund     │ ❌ 0%  │ No implementation        │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ $5 cancellation fee logging       │ ❌ 0%  │ No implementation        │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ Driver dispatch post-Start        │ ❌ 0%  │ No implementation        │

├───────────────────────────────────┼────────┼──────────────────────────┤

│ Clerk webhook handlers            │ ❌ 0%  │ No webhook endpoint      │

└───────────────────────────────────┴────────┴──────────────────────────┘

Multi-Tenancy / White Label — 0% complete

┌─────────────────────────────────┬────────┬──────────────────────────────────────┐

│             Feature             │ Status │                Notes                 │

├─────────────────────────────────┼────────┼──────────────────────────────────────┤

│ Multi-event architecture        │ ❌ 0%  │ Single hardcoded dataset             │

├─────────────────────────────────┼────────┼──────────────────────────────────────┤

│ Super admin vs event operator   │ ❌ 0%  │ No role scoping beyond isVendor flag │

├─────────────────────────────────┼────────┼──────────────────────────────────────┤

│ Dynamic branding per event      │ ❌ 0%  │ Static design                        │

├─────────────────────────────────┼────────┼──────────────────────────────────────┤

│ Unique URL/QR per event         │ ❌ 0%  │ No generation system                 │

├─────────────────────────────────┼────────┼──────────────────────────────────────┤

│ Customer app pulls event config │ ❌ 0%  │ No dynamic config                    │

└─────────────────────────────────┴────────┴──────────────────────────────────────┘

---

3. CRITICAL REQUIREMENTS CHECK

❌ Requirement 1: Two-Step Vendor Acceptance

90-second Accept window → 2-minute Start window → Driver dispatch

Auto-cancel + instant refund if either window missed

Status: ❌ 0% — Not implemented

There is no mechanism for this anywhere in the codebase. The VendorDashboard has status buttons (Accept, Start, etc.) in the UI, but:

- No countdown timers

- No timer state management

- No backend to enforce the windows

- No Firebase to push status changes to the driver

- No Stripe refund calls

- Driver dispatch doesn't exist at all

This is the single most technically complex feature in the spec. It requires: a server-side timer job, Firebase Realtime for sub-second push, Stripe

refund API, and a coordinated state machine across vendor, driver, customer, and admin views simultaneously.

❌ Requirement 2: Instant Driver Cancellation Notification

Firebase Realtime (<1 second) when vendor cancels post-Start

Customer full refund

$5 cancellation fee logged against vendor

Status: ❌ 0% — Not implemented

Firebase isn't even installed (npm list firebase would return nothing). No service workers. No pub/sub. No notification infrastructure of any kind.

---

4. GAP ANALYSIS — WHAT'S MISSING

Missing Backend Components

- No server — need Node.js/Express or Next.js API routes

- No database — need PostgreSQL or similar (schema: users, vendors, menu_items, orders, order_items, drivers, events, driver_locations,

cancellations)

- No ORM — need Prisma or Drizzle

- No auth webhooks — Clerk user creation needs to sync to your DB

- No job scheduler — needed for 90s/2m timer enforcement (BullMQ or similar)

Missing Database Tables (estimated minimum)

events              — multi-tenant event config, branding, GPS boundaries

vendors             — vendor profiles, status, option A/B type

menu_items          — items with inStock boolean, vendorId FK

orders              — full order lifecycle state machine

order_items         — line items

drivers             — driver profiles, go-active status

driver_locations    — real-time GPS (or Firebase collection)

cancellations       — vendor cancellation log, $5 fee records

payouts             — Stripe payout tracking

Missing API Endpoints (minimum viable set)

POST /api/orders                  — create order + Stripe charge

PATCH /api/orders/:id/accept      — vendor Accept (start 90s timer)

PATCH /api/orders/:id/start       — vendor Start Order (dispatch driver)

PATCH /api/orders/:id/cancel      — vendor cancel (refund + $5 fee)

GET  /api/vendors/:id/menu        — live menu with stock status

PATCH /api/menu-items/:id/stock   — sold-out toggle

PATCH /api/vendors/:id/status     — busy toggle

GET  /api/drivers/available       — dispatch system

PATCH /api/drivers/:id/location   — GPS update

POST /api/admin/events            — event creation

GET  /api/admin/dashboard         — live stats

POST /api/webhooks/clerk          — user sync

POST /api/webhooks/stripe         — payment events

Missing Third-Party Integrations

┌────────────────────────────┬───────────────────────────────────────────────────────┬────────┐

│          Service           │                        Purpose                        │ Effort │

├────────────────────────────┼───────────────────────────────────────────────────────┼────────┤

│ Stripe Connect             │ Payments + vendor payouts + refunds                   │ High   │

├────────────────────────────┼───────────────────────────────────────────────────────┼────────┤

│ Firebase Realtime DB       │ <1s notifications (order status, driver location)     │ Medium │

├────────────────────────────┼───────────────────────────────────────────────────────┼────────┤

│ DoorDash Drive API         │ Option A vendor delivery fulfillment                  │ High   │

├────────────────────────────┼───────────────────────────────────────────────────────┼────────┤

│ Twilio or Firebase FCM     │ Push/SMS notifications                                │ Medium │

├────────────────────────────┼───────────────────────────────────────────────────────┼────────┤

│ Google Maps Directions API │ Driver navigation (different from current Places API) │ Medium │

└────────────────────────────┴───────────────────────────────────────────────────────┴────────┘

Missing UI Components/Pages

- /track page (referenced in routes but not found in scan)

- Admin portal (entirely missing — no files)

- Driver active-delivery screen

- Live order status for customer (real-time updates)

- Event configuration screen

- White-label customization preview

---

5. PAYMENT MILESTONE STATUS

Milestone 1 — Backend Foundation ($2,500)

┌────────────────────────────┬───────────────────┐

│        Deliverable         │      Status       │

├────────────────────────────┼───────────────────┤

│ Database schema complete   │ ❌ 0%             │

├────────────────────────────┼───────────────────┤

│ API endpoints operational  │ ❌ 0%             │

├────────────────────────────┼───────────────────┤

│ Stripe Connect initialized │ ❌ 0%             │

├────────────────────────────┼───────────────────┤

│ Clerk webhook integration  │ ❌ 0%             │

├────────────────────────────┼───────────────────┤

│ Overall Milestone 1        │ ~0% — Not started │

└────────────────────────────┴───────────────────┘

Milestone 2 — Order System & Vendor Portal ($2,500)

┌───────────────────────────────────────┬──────────────────────┐

│              Deliverable              │        Status        │

├───────────────────────────────────────┼──────────────────────┤

│ Order lifecycle implemented (backend) │ ❌ 0%                │

├───────────────────────────────────────┼──────────────────────┤

│ Vendor portal UI built                │ ✅ 70% (UI only)     │

├───────────────────────────────────────┼──────────────────────┤

│ Real-time notifications working       │ ❌ 0%                │

├───────────────────────────────────────┼──────────────────────┤

│ Payment processing functional         │ ❌ 0%                │

├───────────────────────────────────────┼──────────────────────┤

│ Overall Milestone 2                   │ ~18% — UI shell only │

└───────────────────────────────────────┴──────────────────────┘

Milestone 3 — Driver System ($2,500)

┌───────────────────────────┬────────────────────────┐

│        Deliverable        │         Status         │

├───────────────────────────┼────────────────────────┤

│ Driver onboarding wizard  │ ✅ 85%                 │

├───────────────────────────┼────────────────────────┤

│ Driver active-session app │ ❌ 0%                  │

├───────────────────────────┼────────────────────────┤

│ GPS tracking integrated   │ ❌ 0%                  │

├───────────────────────────┼────────────────────────┤

│ Order matching algorithm  │ ❌ 0%                  │

├───────────────────────────┼────────────────────────┤

│ Overall Milestone 3       │ ~15% — Onboarding only │

└───────────────────────────┴────────────────────────┘

Milestone 4 — Admin & Launch ($2,500)

┌─────────────────────────────┬───────────────────┐

│         Deliverable         │      Status       │

├─────────────────────────────┼───────────────────┤

│ Admin portal complete       │ ❌ 0%             │

├─────────────────────────────┼───────────────────┤

│ Multi-event architecture    │ ❌ 0%             │

├─────────────────────────────┼───────────────────┤

│ White-label branding system │ ❌ 0%             │

├─────────────────────────────┼───────────────────┤

│ Overall Milestone 4         │ ~0% — Not started │

└─────────────────────────────┴───────────────────┘

---

6. PRIORITIZED ACTION PLAN

Must Do Now — Weeks 1–3 (Blocking everything)

┌─────────────────────────────────────────────────────────────────────────────────┬───────┬───────────────────────────────────────────┐

│                                      Task                                       │ Hours │               Why blocking                │

├─────────────────────────────────────────────────────────────────────────────────┼───────┼───────────────────────────────────────────┤

│ Choose and set up backend (Next.js API routes recommended — no separate server) │ 8h    │ Everything else runs on this              │

├─────────────────────────────────────────────────────────────────────────────────┼───────┼───────────────────────────────────────────┤

│ Set up PostgreSQL + Prisma schema (all tables)                                  │ 16h   │ No data persistence without this          │

├─────────────────────────────────────────────────────────────────────────────────┼───────┼───────────────────────────────────────────┤

│ Clerk webhook → DB user sync                                                    │ 6h    │ Orders need a real user record            │

├─────────────────────────────────────────────────────────────────────────────────┼───────┼───────────────────────────────────────────┤

│ Stripe Connect initialization + test mode                                       │ 12h   │ Can't test order flow without payments    │

├─────────────────────────────────────────────────────────────────────────────────┼───────┼───────────────────────────────────────────┤

│ Firebase project setup + Realtime DB rules                                      │ 8h    │ Two-step timer notifications require this │

├─────────────────────────────────────────────────────────────────────────────────┼───────┼───────────────────────────────────────────┤

│ Total                                                                           │ ~50h  │                                           │

└─────────────────────────────────────────────────────────────────────────────────┴───────┴───────────────────────────────────────────┘

Do Next — Weeks 3–6 (Critical path)

┌──────────────────────────────────────────┬───────┬──────────────────────────────────────────────────────┐

│                   Task                   │ Hours │                        Notes                         │

├──────────────────────────────────────────┼───────┼──────────────────────────────────────────────────────┤

│ Order creation API + Stripe charge       │ 16h   │ Core transaction                                     │

├──────────────────────────────────────────┼───────┼──────────────────────────────────────────────────────┤

│ Two-step vendor acceptance state machine │ 24h   │ Most complex feature — server timers + Firebase push │

├──────────────────────────────────────────┼───────┼──────────────────────────────────────────────────────┤

│ Vendor dashboard wired to real API       │ 20h   │ Replace vendorPortalData.js                          │

├──────────────────────────────────────────┼───────┼──────────────────────────────────────────────────────┤

│ Sold-out toggle + Busy toggle (live)     │ 8h    │ Vendor critical path                                 │

├──────────────────────────────────────────┼───────┼──────────────────────────────────────────────────────┤

│ Customer order status tracking page      │ 16h   │ Needs Firebase subscription                          │

├──────────────────────────────────────────┼───────┼──────────────────────────────────────────────────────┤

│ Auto-cancel + Stripe refund logic        │ 12h   │ Required per spec                                    │

├──────────────────────────────────────────┼───────┼──────────────────────────────────────────────────────┤

│ Total                                    │ ~96h  │                                                      │

└──────────────────────────────────────────┴───────┴──────────────────────────────────────────────────────┘

Do After — Weeks 6–9

┌─────────────────────────────────────────────────┬───────┬───────────────────────────┐

│                      Task                       │ Hours │           Notes           │

├─────────────────────────────────────────────────┼───────┼───────────────────────────┤

│ Driver active-session app (GPS + 2-leg nav)     │ 32h   │ Full driver flow          │

├─────────────────────────────────────────────────┼───────┼───────────────────────────┤

│ Admin portal MVP (event setup + live dashboard) │ 40h   │ Client deliverable        │

├─────────────────────────────────────────────────┼───────┼───────────────────────────┤

│ DoorDash Drive API integration (Option A)       │ 20h   │ Vendor type A fulfillment │

├─────────────────────────────────────────────────┼───────┼───────────────────────────┤

│ Push notifications (FCM)                        │ 16h   │ Customer/driver alerts    │

├─────────────────────────────────────────────────┼───────┼───────────────────────────┤

│ Multi-event architecture (DB + routing)         │ 24h   │ Multi-tenancy             │

├─────────────────────────────────────────────────┼───────┼───────────────────────────┤

│ Total                                           │ ~132h │                           │

└─────────────────────────────────────────────────┴───────┴───────────────────────────┘

Do Last — Weeks 9–11

┌─────────────────────────────────┬───────┬───────────────────────────┐

│              Task               │ Hours │           Notes           │

├─────────────────────────────────┼───────┼───────────────────────────┤

│ White-label branding per event  │ 16h   │ CSS variables + DB config │

├─────────────────────────────────┼───────┼───────────────────────────┤

│ Post-event report generation    │ 12h   │ Admin analytics           │

├─────────────────────────────────┼───────┼───────────────────────────┤

│ Stripe payout triggering UI     │ 8h    │ Admin action              │

├─────────────────────────────────┼───────┼───────────────────────────┤

│ Unique URL/QR per event         │ 8h    │ Marketing tool            │

├─────────────────────────────────┼───────┼───────────────────────────┤

│ Tablet layout polish for vendor │ 12h   │ UX requirement            │

├─────────────────────────────────┼───────┼───────────────────────────┤

│ End-to-end testing + bug fixes  │ 24h   │ Launch prep               │

├─────────────────────────────────┼───────┼───────────────────────────┤

│ Total                           │ ~80h  │                           │

└─────────────────────────────────┴───────┴───────────────────────────┘

Grand total: ~358 estimated hours of remaining work

---

7. TECHNOLOGY GAPS

Install Immediately

# Backend runtime (if using Next.js API routes — recommended)

npm install next  # or keep Vite + add Express

# Database

npm install prisma @prisma/client

npm install postgres  # or pg

# Payments

npm install stripe

# Real-time

npm install firebase

# Job queue (for 90s/2m timers)

npm install bullmq ioredis

# Analytics charts

npm install recharts

# Validation

npm install zod

Infrastructure to Provision

┌───────────────────────────┬─────────────────────┬───────────┬───────────┐

│          Service          │      Provider       │  Cost/mo  │ Priority  │

├───────────────────────────┼─────────────────────┼───────────┼───────────┤

│ PostgreSQL                │ Supabase or Railway │ Free–$10  │ Immediate │

├───────────────────────────┼─────────────────────┼───────────┼───────────┤

│ Redis (for BullMQ timers) │ Upstash             │ Free–$5   │ Immediate │

├───────────────────────────┼─────────────────────┼───────────┼───────────┤

│ Firebase (Realtime DB)    │ Google              │ Free tier │ Immediate │

├───────────────────────────┼─────────────────────┼───────────┼───────────┤

│ Stripe account            │ Stripe              │ % per txn │ Immediate │

├───────────────────────────┼─────────────────────┼───────────┼───────────┤

│ Server hosting            │ Vercel/Railway      │ $0–$20    │ Week 1    │

└───────────────────────────┴─────────────────────┴───────────┴───────────┘

---

8. RISK FLAGS

🔴 Critical Risks

1. Timeline is not survivable at current pace. ~358 hours of work in 11 weeks = ~33 hours/week. Possible solo only if full-time. If part-time, June 1

is unrealistic.

2. Two-step vendor timer is architectural, not incremental. It requires Firebase + server-side jobs + Stripe refunds + coordinated real-time state —

all built correctly the first time. Getting this wrong means the entire order flow breaks.

3. Milestone 1 hasn't started. The contract shows Milestone 1 is the prerequisite for everything. At 0% completion, Milestones 2–4 are all blocked.

🟡 Significant Risks

4. DoorDash Drive API integration is external and unpredictable. Their API requires business verification and has rate limits. Start the application

process now.

5. Stripe Connect Express accounts require identity verification per vendor. This is a multi-day onboarding process per vendor, not an instant API

call.

6. Multi-tenancy is a schema decision you must make in Week 1. Retrofitting multi-tenancy after the DB is built is extremely costly. Design all

tables with event_id foreign keys from day one.

7. The isVendor flag in Clerk's unsafeMetadata is a security risk. Vendor authorization should come from your own database after the backend is

built, not from unverified client metadata.

🟢 Assets Worth Noting

- The frontend quality is genuinely high — consistent design system, good UX patterns, production-ready aesthetics. This work won't need to be

redone.

- BecomeVendor.jsx and BecomeDriver.jsx are solid onboarding wizards that can be wired to backend APIs.

- VendorDashboard.jsx UI shell saves meaningful time — you just need to replace mock data with real API calls.

- Clerk is already integrated well. Webhooks are the only missing piece.

---

Recommended Next 3 Sprints

Sprint 1 (Now — Week 3): "Turn On The Lights"

Set up Next.js API routes (or Express), Prisma + PostgreSQL, Stripe Connect test mode, Firebase project, and Clerk webhook. Goal: a single real order

can be created and stored in the database with a real Stripe charge.

Sprint 2 (Week 3–6): "Make Orders Work"

Implement the full order lifecycle — creation, two-step vendor acceptance with timers, Firebase push to driver, auto-cancellation with Stripe refund.

Wire VendorDashboard to real data. Goal: a vendor can receive and accept a real order, and a driver gets dispatched.

Sprint 3 (Week 6–9): "Build The Driver App + Admin MVP"

Complete driver active-session flow (GPS, 2-leg navigation, pickup/dropoff confirmation) and build the admin portal MVP (event setup, live dashboard,

vendor/driver management). Goal: a complete end-to-end order can be placed, fulfilled, and monitored.

22 Mar

🎯 FairSynq — Revised 7-Part Master Plan

Updated: March 2026 | Starting point: ~14% complete

---

PART 1: ✅ COMPLETE — Next.js Migration

Next.js 14 App Router, SPA catch-all, ClerkProvider architecture, dev environment. Nothing outstanding.

---

PART 2: ✅ COMPLETE — Database + Core Backend Infrastructure

PostgreSQL/Supabase connected, Prisma schema live, Clerk webhook syncing users, Stripe/Firebase Admin initialized, core

read APIs (vendors, menu, events) functional. Webhook handlers wired.

What's NOT done from the original Part 2 scope — carried forward intentionally:

- Firebase Realtime DB actual reads/writes (Part 3)

- BullMQ worker processes (Part 3)

- Offline buffering implementation (Part 7)

---

PART 3: 🔴 Schema V2 + Core Transaction Flow

Dependency anchor — everything from Part 4 onward is blocked until this is done.

3.1 — Platform Rename (Day 1 quick win)

- Global find-replace FairDash → FairSynq across all JSX, TSX, metadata, emails

- Update app/layout.tsx title and description

- Update NEXT_PUBLIC_APP_URL references

3.2 — Schema V2 (Prisma migration)

All addendum V2 structural changes in one migration:

- MenuItem — add prepTime Int (minutes, required, non-null)

- Order — add fulfillmentType FulfillmentType enum (BOOTH_PICKUP, CURBSIDE, HOME_DELIVERY)

- Order — add vehicleMake, vehicleColor, vehiclePlate (nullable Strings for curbside)

- Order — add deliveryFee Float (nullable, home delivery only), deliveryStreet, deliveryCity, deliveryZip

- Order — add UNDELIVERABLE to OrderStatus enum (home delivery unreachable)

- Event — replace isActive Boolean with EventStatus enum (ACTIVE, UPCOMING, INACTIVE)

- Event — add eventLat Float, eventLng Float (for discovery distance calculations — separate from stagingZone coords)

- Event — add curbsideZoneLat, curbsideZoneLng, curbsideZoneDescription, curbsideMethod enum (RUNNER_DELIVERS,

CUSTOMER_WALKS)

- Event — add homeDeliveryFee Float, homeDeliveryRadiusKm Float, runnerTransportDescription

- New FulfillmentConfig model (per event: boothPickupEnabled, curbsideEnabled, homeDeliveryEnabled — booleans with all

related config)

3.3 — Order Creation API

POST /api/orders — the most critical missing endpoint in the entire system:

- Validate cart items against live DB (prices, availability, vendor online status)

- Enforce fulfillment type is enabled for the event

- Calculate: subtotal, fairDashFee = subtotal × 0.07, deliveryFee (if HOME_DELIVERY), total

- Create Stripe PaymentIntent with application_fee_amount on the subtotal only

- Write Order + OrderItems to DB with status PLACED

- Write order event to Firebase Realtime DB (triggers vendor notification)

- Return clientSecret to frontend for Stripe Elements confirmation

3.4 — Order State Machine

PATCH /api/orders/:id/status — vendor-auth required:

- Valid transitions: PLACED → ACCEPTED → PREPARING → READY → COMPLETED

- On READY: schedule BullMQ delayed job for UNCOLLECTED (15 min for booth/curbside)

- On COMPLETED: trigger Stripe transfer to vendor (stripe.transfers.create) for vendorPayout amount

- On CANCELLED: initiate Stripe refund, write Cancellation record

- All status changes write to Firebase Realtime DB

3.5 — Checkout Flow (Phase 1 — Booth Pickup only)

Rewrite Checkout.jsx to be API-connected for booth pickup first:

- Call POST /api/orders on submit

- Stripe Elements for card capture (replace mock payment fields)

- Order confirmation screen with order ID

- Poll Firebase or order status endpoint for live status updates

3.6 — Customer Order Tracking

New /track/:orderId view (currently a ComingSoon stub):

- Real-time status updates via Firebase Realtime DB listener

- Status timeline (Placed → Accepted → Preparing → Ready → Collected)

- Vendor booth number for pickup

3.7 — BullMQ Worker Setup

- Define order-timers queue

- Worker: UNCOLLECTED job (fires 15 min after READY for booth pickup) → set status UNCOLLECTED, no refund

- Worker: insurance-expiry cron (daily check → flip insuranceExpired = true)

- Redis connection via REDIS_URL

Deliverable: First real end-to-end order can be placed, paid, accepted by vendor, and completed.

---

PART 4: 🔴 Fulfillment System + Runner App

Depends on Part 3 being complete. Booth Pickup must work before adding Curbside and Home Delivery.

4.1 — Fulfillment Configuration API

- GET /api/events/:slug/fulfillment — returns which types are enabled + their config

- PATCH /api/events/:slug/fulfillment — admin auth, updates config

- Validation: cannot enable Curbside without GPS pin + text description both set

4.2 — Checkout Fulfillment Selector

Update Checkout.jsx:

- Fetch event fulfillment config on load

- If only one type enabled → auto-select, skip selector entirely

- If multiple → render selection cards (Booth Pickup / Curbside / Home Delivery)

- Conditional form sections rendered based on selection:

- Curbside: vehicle make, color, license plate + curbside zone text description display

- Home Delivery: Google Maps address autocomplete (street, city, zip) + delivery fee line item

- Pass fulfillmentType + type-specific fields to POST /api/orders

4.3 — Curbside Pickup

- Estimated ready time at checkout (sum of prepTime across cart items)

- Push notification when order status → READY (Firebase Cloud Messaging)

- Curbside no-show: BullMQ job (10 min after READY for curbside) → UNCOLLECTED, no refund

- Runner app curbside queue (see 4.5)

4.4 — Home Delivery

- Delivery radius enforcement: calculate distance from eventLat/Lng to customer address at checkout. Reject if outside

homeDeliveryRadiusKm

- Delivery fee: separate line item, passed through to event operator's Stripe account (NOT subject to 7% fee)

- Home delivery payout: stripe.transfers.create for delivery fee → event operator Stripe account; separate transfer of

vendorPayout to vendor account

- Unreachable customer: BullMQ job (10 min after READY for home delivery) — Runner marks UNDELIVERABLE, no refund

- Full push notification set: accepted → picked up from booth → on the way → delivered

4.5 — Runner App

New protected route /runner (event-staff role only):

- Authentication: Clerk role = 'runner' in publicMetadata

- Curbside queue: orders with fulfillmentType = CURBSIDE assigned to this event, ordered by readyAt

- Shows vehicle details (make, color, plate)

- GPS navigation link → curbsideZoneLat/Lng

- "Delivered to Car" / "Customer at Window" action button

- Home Delivery queue: orders with fulfillmentType = HOME_DELIVERY

- Two-leg navigation: current location → vendor booth number → customer address

- "Picked Up from Booth" action + "Delivered" action

- Contact customer button

- Real-time location broadcast: Runner app writes GPS coords to Firebase Realtime DB every 5 seconds during active

delivery

- Customer order tracking page reads Runner coords and renders on Google Maps

Deliverable: All three fulfillment types functional end-to-end. Runners can manage curbside and home delivery orders.

---

PART 5: 🔴 Vendor System

Depends on Part 3 for live order data. Part 4 fulfillment labels need to be in place.

5.1 — VendorDashboard → Live Data

Replace every vendorPortalData.js import with real API calls:

- KPI stats: GET /api/vendors/:id/stats (today's revenue, order count, avg order value)

- Order queue: GET /api/orders?vendorId=&status=PLACED,ACCEPTED,PREPARING,READY + Firebase listener for real-time new

orders (push new card without refresh)

- Revenue chart: GET /api/vendors/:id/revenue?period=7d|30d|90d

- All orders table: GET /api/orders?vendorId=&page=&limit=

5.2 — Vendor Dashboard UI Updates

- Add fulfillment type badge (Booth Pickup / Curbside / Home Delivery) to every order card

- Wire "Open / Closed" toggle to PATCH /api/vendors/:id with isOffline

- Wire "Busy" toggle to PATCH /api/vendors/:id with isBusy

- New order audio/visual alert (Firebase listener triggers notification in-app)

5.3 — Vendor Menu Manager

Full CRUD UI inside VendorDashboard (not a separate page):

- Item list with available/sold-out toggle → PATCH /api/menu/:id with isAvailable

- Add item form: name (required), photo upload, price (required), prepTime in minutes (required), category

- Edit item in-place

- Delete with confirmation → DELETE /api/menu/:id

- File upload: presigned URL from Supabase Storage for photos

5.4 — 10-Step Vendor Onboarding Wizard

Expand BecomeVendor.jsx from 4 steps to 10. Wire final submit to POST /api/vendors:

┌──────┬───────────────────────────────────────────────────────────────────────────────────────────────────────────────┐

│ Step │                                                    Content                                                    │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 1    │ Business info (name, cuisine type, description, booth number)                                                 │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 2    │ Contact info (owner name, email, phone, website)                                                              │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 3    │ Menu items — add initial items with name, price, prepTime, photo                                              │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 4    │ Food handler permit upload (required) → Supabase Storage                                                      │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 5    │ Insurance certificate upload (required) + expiry date picker                                                  │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 6    │ Booth photos upload (up to 5)                                                                                 │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 7    │ Stripe Connect — "Connect Your Bank Account" → redirect to Stripe hosted onboarding, webhook confirms         │

│      │ stripeVerified = true                                                                                         │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 8    │ Availability & schedule (which event days operating)                                                          │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 9    │ Terms & conditions agreement                                                                                  │

├──────┼───────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│ 10   │ Review & submit → POST /api/vendors (status = PENDING)                                                        │

└──────┴───────────────────────────────────────────────────────────────────────────────────────────────────────────────┘

5.5 — Stripe Connect Onboarding API

- POST /api/stripe/connect/onboard — creates Stripe Connect Express account, returns hosted onboarding URL

- GET /api/stripe/connect/return — called after Stripe redirect, confirms account status, updates stripeVerified

Deliverable: Vendors can self-onboard completely. Dashboard shows live orders with real-time updates.

---

PART 6: 🔴 Admin Portal + Smart Customer Landing Page

Depends on fulfillment config (Part 4) and vendor approval schema (Part 2). Largely independent of Part 5.

6.1 — Admin Portal (New protected section /admin)

Role-gated: Clerk publicMetadata.role = 'admin' or 'super_admin'

Event Operator tools (scoped to one event):

- Event dashboard: live order count, revenue today, vendor status grid (open/busy/offline)

- Vendor management: applications list (PENDING), approve → ACTIVE / reject → REJECTED with reason

- Fulfillment configuration UI:

- Booth Pickup: on/off toggle

- Curbside: on/off, Google Maps GPS pin drop for curbside zone, text description field, Runner/Window method toggle.

Cannot enable without both coordinates + description

- Home Delivery: on/off, delivery radius (km) number input, delivery fee ($) input, runner transport description text

field

- Go Live button (sets EventStatus → ACTIVE)

- Close Event button (sets EventStatus → INACTIVE, stops new orders)

- Runner account management (invite staff, assign runner role)

Super Admin tools (platform-wide):

- All events list with status

- Event creation wizard

- Operator account assignment

6.2 — Admin APIs

- GET/PATCH /api/admin/events/:id/status — go live / close

- GET /api/admin/vendors?status=PENDING — applications queue

- PATCH /api/admin/vendors/:id/approve and /reject

- GET /api/admin/dashboard — platform-wide stats (super admin only)

6.3 — Smart Customer Landing Page (4 Scenarios)

Rewrite Landing.jsx with scenario-based logic:

┌─────────────────────────┬───────────────────────────────────────┬──────────────────────────────────────────────────┐

│        Scenario         │                Trigger                │                     Behavior                     │

├─────────────────────────┼───────────────────────────────────────┼──────────────────────────────────────────────────┤

│ QR scan                 │ URL contains event slug               │ Load event page directly, skip discovery         │

├─────────────────────────┼───────────────────────────────────────┼──────────────────────────────────────────────────┤

│ Direct event URL        │ fairsynq.com/[slug]                   │ Load white-label event page                      │

├─────────────────────────┼───────────────────────────────────────┼──────────────────────────────────────────────────┤

│ Root URL with location  │ Geolocation granted                   │ Show nearby active events as cards               │

├─────────────────────────┼───────────────────────────────────────┼──────────────────────────────────────────────────┤

│ Root URL, no nearby     │ Geolocation returns nothing within    │ "No events near you" + search bar + upcoming     │

│ events                  │ radius                                │ events map                                       │

└─────────────────────────┴───────────────────────────────────────┴──────────────────────────────────────────────────┘

Event discovery cards: event name, location description, distance (calculated from user coords), status badge (Active Now

/ This Weekend / Coming Soon mapped from EventStatus enum).

Search: GET /api/events?q=&lat=&lng=&radius= — supports name/city text search and proximity filter.

6.4 — White-Label Event Pages

New dynamic route app/[eventSlug]/page.tsx:

- Fetch event by slug on load

- Apply primaryColor as CSS custom property (--brand-primary)

- Render event logo from logoUrl

- Show only that event's vendors and menu

- Same Menu/Vendor browse UX as current /menu and /vendors but scoped to event

6.5 — QR Code Generation

- On event creation → generate QR code pointing to fairsynq.com/[slug]

- Use qrcode npm package, store data URL in qrCodeUrl field

- Admin portal: display QR code with download button

Deliverable: Admin operators can configure and launch events. Customers can discover events or land directly via QR.

---

PART 7: 🔴 Production Ready

Depends on all prior parts. Final hardening pass before go-live.

7.1 — PWA + Offline First

- next-pwa or custom service worker

- Cache strategy: static assets (stale-while-revalidate), API responses (network-first with fallback)

- Offline order queue: if customer attempts checkout with no connectivity, queue locally and replay on reconnect via

BullMQ

- Offline vendor dashboard: show cached order state, queue status updates for sync on reconnect

7.2 — Push Notifications (FCM)

- Request notification permission on first order

- Firebase Cloud Messaging token stored on User record

- Notification triggers: order accepted, order ready (booth), curbside ready, delivery picked up, delivery on the way,

delivered

- Vendor notifications: new order received (with order details)

7.3 — SMS / OTP Verification (pending client confirmation)

- If confirmed: Twilio OTP on first order only

- Returning customers re-verify via phone number on each order

- Guest checkout available, no OTP

- OTP expires in 5 minutes

- POST /api/auth/otp/send and POST /api/auth/otp/verify

7.4 — Performance

- Image optimization (Supabase CDN or Cloudflare for vendor/menu photos)

- API response caching for event config and menu data (Redis via ioredis)

- Database query optimization (confirm all indexes from schema are being hit)

- Lighthouse audit → target 90+ on mobile

7.5 — Security Hardening

- Rate limiting on order creation and OTP endpoints (Redis sliding window)

- Input validation with Zod on all POST/PATCH bodies (currently missing from most routes)

- Webhook signature verification already done (Clerk + Stripe) ✅

- Delivery radius server-side enforcement (cannot be bypassed client-side)

- Stripe idempotency keys on PaymentIntent creation

7.6 — Testing

- Unit tests for fee calculation logic (subtotal × 0.07, delivery fee pass-through)

- Integration tests for order state machine (all valid and invalid transitions)

- E2E tests (Playwright): place order → vendor accepts → complete → payout recorded

- Load test order creation endpoint (BullMQ queue behavior under concurrent orders)

7.7 — Deployment + Monitoring

- Vercel production deployment with environment variables

- Supabase production project (separate from dev)

- Sentry error monitoring (frontend + API routes)

- Uptime monitoring on /api/health

- Firebase Realtime DB security rules (restrict reads/writes by auth role)

- Stripe webhook endpoint registered in production dashboard

- Clerk webhook endpoint registered in production dashboard

- Post-deploy smoke test checklist

7.8 — Documentation

- Vendor onboarding guide (PDF for event operators to distribute)

- Admin portal user guide

- Runner app quick-start card

- API documentation (auto-generated or Postman collection)

---

Summary View

┌─────────────────────────────┬──────────────────┬──────────────────────────────────────────────────┬────────────────┐

│            Part             │      Status      │                 Core Deliverable                 │   Estimated    │

│                             │                  │                                                  │     Scope      │

├─────────────────────────────┼──────────────────┼──────────────────────────────────────────────────┼────────────────┤

│ 1 — Next.js Migration       │ ✅ Done          │ Working Next.js app                              │ —              │

├─────────────────────────────┼──────────────────┼──────────────────────────────────────────────────┼────────────────┤

│ 2 — DB + Backend Infra      │ ✅ Done          │ Live DB, core APIs, webhooks                     │ —              │

├─────────────────────────────┼──────────────────┼──────────────────────────────────────────────────┼────────────────┤

│ 3 — Schema V2 + Order       │ 🔴 Next          │ First real end-to-end order placed and paid      │ Large          │

│ System                      │                  │                                                  │                │

├─────────────────────────────┼──────────────────┼──────────────────────────────────────────────────┼────────────────┤

│ 4 — Fulfillment + Runner    │ 🔴 Blocked by 3  │ All 3 fulfillment types working, Runner app live │ Large          │

├─────────────────────────────┼──────────────────┼──────────────────────────────────────────────────┼────────────────┤

│ 5 — Vendor System           │ 🔴 Blocked by 3  │ Live dashboard, 10-step onboarding, menu manager │ Medium         │

├─────────────────────────────┼──────────────────┼──────────────────────────────────────────────────┼────────────────┤

│ 6 — Admin + Landing Page    │ 🔴 Blocked by 4  │ Operators can launch events, customers can       │ Large          │

│                             │                  │ discover                                         │                │

├─────────────────────────────┼──────────────────┼──────────────────────────────────────────────────┼────────────────┤

│ 7 — Production Ready        │ 🔴 Blocked by    │ PWA, offline, security, testing, deployed        │ Medium         │

│                             │ all              │                                                  │                │

└─────────────────────────────┴──────────────────┴──────────────────────────────────────────────────┴────────────────┘

Part 3 is the only dependency blocker right now. Nothing in Parts 4–7 can be completed until a real order can be placed.

✻ Baked for 2m 27s